## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2021-08-23 | 6 | 2021-08-28 | 5 | 6 | Ongoing | 2021-10-15 | Documentación Inicial | 120%
#DIV/0!
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
0 | 2021-08-23 | 6 | 2021-08-28 | 0.5 | 1 | Released | 2021-10-15 | Product Backlog priorizado | 1
0 | 2021-08-23 | 6 | 2021-08-28 | 0.25 | 0.5 | Released | 2021-10-15 | Repositorio (GitHub) donde integrarán el trabajo | 1 | #VALUE!
0 | 2021-08-23 | 6 | 2021-08-28 | 0.5 | 1 | Released | 2021-10-15 | Instalación del entorno de desarrollo | 1 | #VALUE!
0 | 2021-08-23 | 6 | 2021-08-28 | 0.5 | 1 | Released | 2021-10-15 | Historias de usuario a desarrollar en el Sprint 1 | 1 | #VALUE!
0 | 2021-08-23 | 6 | 2021-08-28 | 1 | 2 | Released | 2021-10-15 | DevOps(Scrumboard y tareas) | 1 | 100%
0 | 2021-08-23 | 6 | 2021-08-28 | 0.5 | 1 | Released | 2021-10-15 | Mockups | 1
0 | 2021-08-23 | 6 | 2021-08-28 | 0.5 | 1 | Released | 2021-10-15 | Diagrama UML por casos de uso | 1
0 | 2021-08-23 | 6 | 2021-08-28 | 1.5 | 6 | Released | 2021-10-15 | Documentacion de software | 1
#REF! | #REF! |  | #REF! | #REF! |  | #REF!
#REF! | #REF! |  | #REF! | #REF! |  | #REF!
#REF! | #REF! |  | #REF! | #REF! |  | #REF!
#REF! | #REF! |  | #REF! | #REF! |  | #REF!
#REF! | #REF! |  | #REF! | #REF! |  | #REF!
#REF! | #REF! |  | #REF! | #REF! |  | #REF!
|  |  | Unallocated stories | #VALUE!
|  |  | Total Size | #REF! | 13
Formulas:
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Product Backlook | Ongoing | 3 | 0 | 5 | Planificación | Se realizó según la planeación | Sin Impacto
2 | Repositorio (GitHub) | Done | 8 | 0 | 5 | Planificación | Se realizó según la planeación | Sin Impacto
3 | Gestión de configuración | Done | 20 | 0 | 4 | Planificación | Se realizó según la planeación | Sin Impacto
4 | Historias de usuario a desarrollar para Sprint 1 | Done | 13 | 0 | 4 | Planificación | Se realizó según la planeación | Sin Impacto
5 | Configuración DevOps | Done | 13 | 0 | 3 | Planificación | Se realizó según la planeación | Sin Impacto
6 | Mookups | Done | 13 | 0 | 2 | Planificación | Se realizó según la planeación | Sin Impacto
7 | UML Casos de uso | Done | 13 | 0 | 2 | Planificación | Se realizó según la planeación | Sin Impacto
8 | Agregar archivo Documentación de software IEEE | Done | 13 | 0 | 1 | Planificación | Se realizó según la planeación | Sin Impacto
8 | Como gestor del proyecto requiero documentacion de software | Done | 1.5 | 1 | 4 | Desarrollo | Elaborar una documentacion,cuya estructura sustente el producto final a entregar
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.